## Repo Checklist
Heady Repo Remediation Checklist
Checklist derived from public repository review. Track completion status and evidence links internally.
Repo/Surface | Issue | Risk Level | Recommended Fix | Owner | Status | Target Sprint | Evidence URL | Notes
heady-docs | Remove or privatize API key/service inventory page | Critical | Delete public file, move to a private internal runbook, and rotate affected credentials | Engineering/Security | Open | Sprint 0 | https://github.com/HeadyMe/heady-docs/blob/main/api/api-keys-reference.md | Treat as immediate remediation
Heady-pre-production | Remove or privatize duplicate API key/service inventory page | Critical | Delete public file, move to a private internal runbook, and rotate affected credentials | Engineering/Security | Open | Sprint 0 | https://github.com/HeadyMe/Heady-pre-production-9f2f0642/blob/main/docs/api-keys-reference.md | Immediate
Deploy workflow | Remove overly permissive deployment success patterns | Critical | Fail pipeline on broken smoke tests and high-risk deploy failures; require approvals where appropriate | Engineering | Open | Sprint 0 | https://github.com/HeadyMe/Heady-pre-production-9f2f0642/blob/main/.github/workflows/deploy.yml | Review continue-on-error use
Cloud Run exposure | Review allow-unauthenticated deployment | High | Restrict access or front with explicit auth/proxy rules where needed | Engineering | Open | Sprint 0 | https://github.com/HeadyMe/Heady-pre-production-9f2f0642/blob/main/.github/workflows/deploy.yml | Public endpoints should be intentionally documented
Auth routes | Reduce token/API key exposure in register/login responses | High | Return minimum necessary payloads and document token handling | Engineering | Open | Sprint 1 | https://github.com/HeadyMe/Heady-pre-production-9f2f0642/blob/main/src/auth/auth-routes.js | Review refresh token and apiKeys exposure
Domains config | Correct malformed canonical hostnames and environment mapping | High | Fix service-domains registry and validate DNS/CORS/cookie alignment | Engineering | Open | Sprint 1 | https://github.com/HeadyMe/Heady-pre-production-9f2f0642/blob/main/configs/_domains/service-domains.yaml | Use one canonical naming pattern
Public legal docs | Missing privacy policy / terms / notice at collection | High | Publish approved legal docs and link them in product surfaces | Legal/Ops | Open | Sprint 1 | https://github.com/HeadyMe/Heady-pre-production-9f2f0642 | Required before broad user onboarding
Retention governance | No visible public/internal retention schedule in reviewed repos | Medium | Adopt and implement retention schedule with deletion workflows and holds | Ops/Security | Open | Sprint 1 | https://github.com/HeadyMe/heady-docs | Coordinate with vendors and logs
Archived public repos | Review archived repos for stale or sensitive operational detail | Medium | Archive privately where possible, sanitize residual docs/configuration | Engineering | Open | Sprint 2 | https://github.com/HeadySystems/Heady | Inventory other public archives too